## B3
2023-03-01
B3 VDU failed during humudity test | Solution on circuit | by When
B3 VDU EMI/EMC test failed | Fiexed job done, wait for final test | 8 Mar. 2023 | Production? | Design for production by Apr. 2023
B3 VCU CE test failed | A power filter added, fly wire on prototype for tetsing. Final production design on PCB (already done on schematic, mechanical design done, wiating for PCB routine) | 8 Mr 2023 , on testing. | Production? | Design for production by Apr. 2023

## Terrex-Gen5
2023-03-01
| pcb routine | PCB fabrication | components purchase | pcb assembly
VCU-Inetrface-card | PCB routine ready | 18 Mar. PCB fab. Complete | 2023-03-24 | 2023-04-15 | expected schedules
VDU-Interface-card | PCB routine ready | 2023-03-08 | 2023-03-24 | 2023-04-15
VSR-B2 | 3 Mar Ready | 2023-03-20 | 2023-03-24 | 2023-04-15
VSR-B1 | 9 Mar Ready | 2023-03-31 | 2023-03-24 | 2023-04-15
iDDP-EXT | 10 Mar Ready | 2023-03-22 | 2023-03-24 | 2023-04-10 | To be finalized, confirmed.
VSR-B3 | completed before 15 Mar | 2023-03-24 | 2023-03-24 | 2023-04-15
VSR-PWR | 2023-03-07 | 2023-03-22 | 2023-03-24 | 2023-04-15
ALINX-ACU7EVB testing | DONE
LCD |  |  | 2023-04-15
Push button part nunmber |  |  | 2023-04-15 |  | Overall BOM fro all
VSR-G5 | Fabrication drawing ready | End of March. PO to be placed |  |  | Thermal fins. To be finalized by Steven and Jacky. Thermal sheet to be purchased. Crews / standard parts to be purchased by Jacky
iDDP-G5 | Fabrication drawing ready | End of March. PO to be placed

## calculations (hidden)
*** This sheet should remain hidden ***
|  |  | Min | 2022-01-01
Max
|  |  | Days | #REF!
|  |  | Date | #REF! | 0
|  |  | Type | #REF!
|  |  | Priority | #REF!
[5 empty] | #VALUE! | #VALUE!
[5 empty] | 30 | 30 | Sorted | Sorted
|  | Date | Opened | Closed | Types | Priorities | Types | Priorities
[5 empty] | * | *
| 1 | #REF! | #REF! | #REF! | #REF! | #REF! | * | *
| 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 31 | #REF! | #REF! | #REF!
| 32 | #REF! | #REF! | #REF!
| 33 | #REF! | #REF! | #REF!
| 34 | #REF! | #REF! | #REF!
| 35 | #REF! | #REF! | #REF!
| 36 | #REF! | #REF! | #REF!
| 37 | #REF! | #REF! | #REF!
| 38 | #REF! | #REF! | #REF!
| 39 | #REF! | #REF! | #REF!
| 40 | #REF! | #REF! | #REF!
| 41 | #REF! | #REF! | #REF!
| 42 | #REF! | #REF! | #REF!
| 43 | #REF! | #REF! | #REF!
| 44 | #REF! | #REF! | #REF!
| 45 | #REF! | #REF! | #REF!
| 46 | #REF! | #REF! | #REF!
| 47 | #REF! | #REF! | #REF!
| 48 | #REF! | #REF! | #REF!
| 49 | #REF! | #REF! | #REF!
| 50 | #REF! | #REF! | #REF!
| 51 | #REF! | #REF! | #REF!
| 52 | #REF! | #REF! | #REF!
| 53 | #REF! | #REF! | #REF!
| 54 | #REF! | #REF! | #REF!
| 55 | #REF! | #REF! | #REF!
| 56 | #REF! | #REF! | #REF!
| 57 | #REF! | #REF! | #REF!
| 58 | #REF! | #REF! | #REF!
| 59 | #REF! | #REF! | #REF!
| 60 | #REF! | #REF! | #REF!
| 61 | #REF! | #REF! | #REF!
| 62 | #REF! | #REF! | #REF!
| 63 | #REF! | #REF! | #REF!
| 64 | #REF! | #REF! | #REF!
| 65 | #REF! | #REF! | #REF!